## Sheet1
Task | Status | Owner | Proof / File | Folder | Definition of Done (DoD) | Deadline
Project initialization & idea | Initial version | Yohann | Initial commit; project idea notes | root / docs | Repo created; basic idea written | 26 Sep
Database structure & UML base | In progress (at that time) | Mayomat, Valentin | Early ERD/table structure; first SQL draft | docs / database | ERD draft + tables draft committed | 10 Oct
Initial Vue skeleton & repo setup | Initial version | Mayomat, Valentin | Vue skeleton (Home/About); folders; .gitignore | frontend / root | Vue app runs; folders created; gitignore added | 17 Oct
Repository structure (front/back/db/docs) | Done | Yohann, Mayomat | Folder tree visible in repo | root | Clean repo, correct folder names | 31 Oct
dev branch pushed & workflow | Done | Mayomat | Branch dev on GitHub | root | Feature branches merge into dev (not main) | 31 Oct
UML Use Case (final) | Done | Mayomat, Valentin, Yohann | docs/UML_UseCase.pdf | docs | Include fixed; 'Choose recipe/date' included | 31 Oct
Gantt (planned) | Done | Mayomat, Yohann | docs/UML_Gantt.xlsx | docs | Milestones M1–M4 listed only by deadlines | 31 Oct
Database schema | Done | Valentin | database/schema.sql | database | All tables created; FKs & constraints ready | 31 Oct
Database seed (test data) | Done | Mayomat | database/schema.sql (with INSERTS) | database | Demo data inserted; importable | 31 Oct
Frontend (fake JSON) | Done | Mayomat | frontend/src/services/fake/*.json | frontend | 3 lists + CRUD in memory; navbar | 31 Oct
README and screenshots | To be done (All) | All | README.md; images in docs/ or README | root / docs | Install/run steps and screenshots included | 1 Nov
Backend skeleton (Express + MySQL) | To be done (All) | All | backend/src/...; .env.example | backend | App, routes, models, db connection, error handler | 3 Nov
UML 2 (Activity + Sequence + Wireframes) | To be done (All) | All | docs/UML_Activity_Sequence_Wireframes.pdf | docs | 2 UML diagrams + 3 wireframes in one PDF | 5 Nov
Final documentation & merge to main | To be done (All) | All | README.md; merged repository | root | Everything integrated; demo-ready | 7 Nov